## Product Backlog
PRODUCT BACKLOG FOR PHASE 2 (ANALYTICS PROJECT)
ID | As a… | I want to be able to… | So that… | Priority(1-5) | Sprint | Hours Required | Status
1 | Manager | I need a graphical user interface to execute prediction of safe and dangerous taxi trips | I can visualise the data easier and gain insight | 1 | 2 | 24 | Done
2 | Administrator | I need to build and optimize machine learning models | I can classify safe and dangerous trips to high accuracy | 1 | 2 | 5 | Done
3 | Administrator | I need to ensure the ratio of safe and dangerous records is almost equal | I will have an unbiased dataset to work with to achieve reliable results from model prediction | 2 | 2 | 120 | Done
4 | Administrator | I need a cleaned Dataset | I would be able to update the records input by future taxi drivers in the app | 2 | 2 | 24 | Done
5 | Administrator | I need to visualise how safe and dangerous trips are classified | I can have a better understanding of how the dataset needs to be classified | 2 | 2 | 6 | Done
6 | Manager | I need cleaned data | I would be able to store the accurate data for future reference | 2 | 2 | 24 | Done
7 | Manager | I need a report | I have a written record of the progress in phase 2 | 3 | 2 | 24 | Done
Total: 207

## Scrum Document
Weeks | Members | Last Week's Progress | This week's Deliverables | Obstacles | Date Updated
Week 11-12 | Jun Hui | Balancing Class Distributions | Finding methods to combat inbalanced class distribution | A lot of different methods to solving inbalanced class distributions which made it hard to decide | 2021-11-11
| Jumana | PCA | PCA | Since the dataset had very few features and scree plot was not showing any distinct elbow, difficult to decide with feature is more important than the other.
| Tushita | Outlier Detection | Outlier Detection | The number of data was very large which made it difficult for the model to load fast.
Outlier Removal
Week 13-14 | Jun Hui | Balancing Class Distributions | Implementing the methods | Logistic regression did not show very valuable information about the performance of the methods | 25/11/2021
Evaluation of the methods
|  |  | Improving the scores | Difficult to think of methods that could be better at balancing the classes
| Jumana | PCA | PCA | Difficult to decide on whether features should be reduced or not.
| Tushita | Outlier Detection and Removal | Outlier Removal | The number of data was very large which made it difficult for the model to load fast.
Week 15-16 | Jun Hui | Balancing Class Distributions | GUI | Did not have enough time to further tune the models and to create more gaphs for evaluation and visualization.
Report ,Powerpoint Slide
Baseline Model (KNN, Decision Tree, Logistic Regression), Tuning model ( KNN, Decision Tree)
| Jumana | PCA | Baseline Models (SGD, Naive Bayes), Tuning Model (SGD) | Too many assignments due at the same time, difficult managing time. Model accuracy was not improving well.
Scrum Document
Report
Powerpoint Slide
| Tushita | EDA for Cleaned Dataset | Report | Too many assignments due at the same time, difficult managing time. Model accuracy was not improving well.
Baseline Models (Random Forest and SVM)
Scrum Document